## Cover
ASCEND LMS
User Acceptance Testing (UAT) Script
Full-Flow Test: Course Creation → Pathway Enrollment → Certificate Download
Project | Ascend LMS
Version | 1.0
Prepared by
Date
Environment
Tested by
Result Legend
PASS
FAIL
BLOCK
N/A
How to use this script
1. Work through each test case in tab order.
2. Execute the Test Steps exactly as written.
3. Compare the actual outcome with the Expected Result.
4. Record PASS / FAIL / BLOCK / N/A in the 'Result' column.
5. Add notes in the 'Actual Result / Notes' column for any FAIL or BLOCK.
6. Use the 'Tester' and 'Date Tested' columns to track who ran each test.

## Test Cases
ASCEND LMS – UAT Test Cases
# | ID | Phase | Role | Feature | Test Steps | Expected Result | Priority | Result | Tester / Date | Actual Result / Notes
▸ 1 – Setup
1 | TC-001 | 1 – Setup | Admin | User Account Activation | Receive activation email → Click activation link → Set password (min. 8 chars) → Click Activate account (Please contact Arfian to get the email content) | Password is set, page shows 'Password set successfully!' and redirects to sign-in page. | Critical
2 | TC-002 | 1 – Setup | Admin | Sign In (Microsoft SSO) | Navigate to the app → Click 'Sign in with Microsoft' → Select existing Microsoft account from picker | User is signed in and redirected to the Home dashboard without re-entering credentials. | Critical
3 | TC-003 | 1 – Setup | Admin | Sign In (Password) | Navigate to sign-in page → Enter email and password → Click Sign in | User is signed in and redirected to the Home dashboard. | Critical
▸ 2 – Admin Setup
4 | TC-004 | 2 – Admin Setup | Admin | Create Office | Admin → Offices → Add Office → Enter office name → Save | Office appears in the office list. | High
5 | TC-005 | 2 – Admin Setup | Admin | Create Topic | Admin → Topics → Add Topic → Enter topic name → Save | Topic appears in the topic list. | High
6 | TC-006 | 2 – Admin Setup | Admin | Create User (manual) | Admin → Users → Add User → Fill name, email, division, title, office → Save | User appears in user list with status Active. | Critical
7 | TC-007 | 2 – Admin Setup | Admin | Bulk Import Users | Admin → Users → Import → Download template → Fill in at least 3 rows (include Manager Email column) → Upload file | Users are created; any assigned managers are linked. Success count shown. | High
8 | TC-008 | 2 – Admin Setup | Admin | Send Activation Email | Admin → Users → Actions (user row) → Send Activation Email | Confirmation shown. User receives activation email within a few minutes. | Critical
9 | TC-009 | 2 – Admin Setup | Admin | Assign Roles to User | Admin → Users → Actions → Assign Roles → Tick 'Manager' and/or 'Trainer' → Save | Role badge appears on the user row. User can now access that role's section. | Critical
10 | TC-010 | 2 – Admin Setup | Admin | Assign Manager to User | Admin → Users → Actions → Assign Managers → Type manager name → Click to add → Close modal | Manager chip appears. User is now linked to that manager. | High
11 | TC-011 | 2 – Admin Setup | Admin | Assign User to Cohort | Admin → Users → Actions → Assign Cohorts → Select cohort → Save | User is listed as a member of the cohort. | Medium
12 | TC-012 | 2 – Admin Setup | Admin | Create Cohort | Admin → Cohorts → Add Cohort → Enter cohort name → Save | Cohort appears in cohort list. | Medium
13 | TC-013 | 2 – Admin Setup | Admin | Create Course (no test/assignment) | Admin → Courses → Add Course → Enter name, description, topic → Save | Course is created with status Published. Appears in course list. | Critical
14 | TC-014 | 2 – Admin Setup | Admin | Assign Trainer to Course | Admin → Courses → [Course] → Manage Contents → Trainers section → Add Trainer → Search trainer name → Assign | Trainer appears in the trainers list for that course. | High
15 | TC-015 | 2 – Admin Setup | Admin | Add Text Content to Course | Admin → Courses → [Course] → Manage Contents → Content tab → Add Content → Type: Text → Enter title and body → Save | Text content item appears in the course content list in correct order. | Critical
16 | TC-016 | 2 – Admin Setup | Admin | Add Video Content to Course | Admin → Courses → [Course] → Content tab → Add Content → Type: Video → Enter title, URL, duration → Save | Video content item appears with correct duration. | High
17 | TC-017 | 2 – Admin Setup | Admin | Add Link Content to Course | Admin → Courses → [Course] → Content tab → Add Content → Type: Link → Enter title and URL → Save | Link content item appears in course. | Medium
18 | TC-018 | 2 – Admin Setup | Admin | Create Test for Course | Admin → Courses → [Course] → Test tab → Create Test → Set pass threshold (e.g. 70%) → Add at least 3 questions (mix types) → Save | Test is saved with the correct threshold and all questions visible. | Critical
19 | TC-019 | 2 – Admin Setup | Admin | Create Assignment for Course | Admin → Courses → [Course] → Assignment tab → Create Assignment → Enter description and SharePoint URL → Save | Assignment is saved and visible with the submission URL. | High
20 | TC-020 | 2 – Admin Setup | Admin | Create Pathway | Admin → Pathways → Add Pathway → Enter name, description, tags → Save | Pathway is created with status Published. | Critical
21 | TC-021 | 2 – Admin Setup | Admin | Add Courses to Pathway | Admin → Pathways → [Pathway] → Add Course → Select course → Set order and points → Save | Course appears in the pathway's course list with correct order and points. | Critical
22 | TC-022 | 2 – Admin Setup | Admin | Set Pathway to Require Approval | Admin → Pathways → [Pathway] → Enable 'Requires Approval' toggle → Save | Pathway shows 'Requires Approval' badge. Learners must request enrollment. | High
23 | TC-023 | 2 – Admin Setup | Admin | Assign Pathway to Cohort | Admin → Cohorts → [Cohort] → Pathways tab → Assign Pathway → Select pathway | Pathway is linked to cohort. All cohort members are auto-enrolled. | High
24 | TC-024 | 2 – Admin Setup | Admin | Draft / Publish Course Toggle | Admin → Courses → [Course] → Manage Contents → Click status toggle to set to Draft → Verify learners cannot see it → Toggle back to Published | Drafted course is hidden from learners. Published course is visible. | Medium
▸ 3 – SME
25 | TC-025 | 3 – SME | SME | Assign SME to Topic | Admin → Topics → [Topic] → SME field → Search user with SME role → Assign | SME is listed under that topic. | High
26 | TC-026 | 3 – SME | SME | View Assigned Topics | Sign in as SME → Subject Matter Expert → My Topics | SME sees all topics they are assigned to and the courses within each topic. | High
27 | TC-027 | 3 – SME | SME | Create Course as SME | SME → My Topics → [Topic] → New Course → Fill details → Save | Course is created under that topic and appears in the course list. | High
28 | TC-028 | 3 – SME | SME | Manage Content as SME | SME → My Topics → [Course] → Add content item → Save | Content item appears in course. Same capability as Trainer. | Medium
▸ 4 – Trainer
29 | TC-029 | 4 – Trainer | Trainer | View Assigned Courses | Sign in as Trainer → Trainer → My Courses | Trainer sees only courses they are assigned to. | High
30 | TC-030 | 4 – Trainer | Trainer | Edit Course Content | Trainer → My Courses → [Course] → Content tab → Edit an existing content item → Save | Content is updated with the new values. | High
31 | TC-031 | 4 – Trainer | Trainer | Edit Test Questions | Trainer → My Courses → [Course] → Test tab → Edit a question → Save | Question is updated correctly. | High
32 | TC-032 | 4 – Trainer | Trainer | Grade Assignment Submission | Trainer → My Courses → [Course] → Submissions tab → Click Grade on a submitted assignment → Select Passed → Add note → Save | Submission status changes to Passed. Learner receives a notification. | Critical
33 | TC-033 | 4 – Trainer | Trainer | Grade Assignment as Failed | Trainer → My Courses → [Course] → Submissions tab → Click Grade → Select Failed → Add note → Save | Submission status changes to Failed. Learner receives a notification. | High
34 | TC-034 | 4 – Trainer | Trainer | View Course Feedback | Trainer → My Courses → [Course] → Feedback tab | Average star rating and individual learner comments are shown. | Medium
▸ 5 – Learner (Self-Enroll)
35 | TC-035 | 5 – Learner (Self-Enroll) | Learner | View Home Dashboard | Sign in as Learner → Home page | Dashboard shows enrolled pathways with progress bars, points, streak, and leaderboard rank. | Critical
36 | TC-036 | 5 – Learner (Self-Enroll) | Learner | Browse Pathways | Learner → Pathways → Browse published pathways | All published pathways are shown with name, description, and tags. | Critical
37 | TC-037 | 5 – Learner (Self-Enroll) | Learner | Self-Enroll in Pathway (no approval) | Learner → Pathways → [Pathway without approval] → Enroll | Learner is immediately enrolled. Pathway appears on Home dashboard. | Critical
38 | TC-038 | 5 – Learner (Self-Enroll) | Learner | Request Enrollment in Pathway (approval required) | Learner → Pathways → [Pathway with approval] → Request Enrollment → Add note → Submit | Request is submitted. Learner sees 'Pending' status. Manager receives notification. | Critical
39 | TC-039 | 5 – Learner (Self-Enroll) | Learner | Open Course Content (Text) | Learner → [Enrolled Pathway] → Open course → Click text content item | Text content is displayed in the main panel. | Critical
40 | TC-040 | 5 – Learner (Self-Enroll) | Learner | Watch Video Content | Learner → Course → Click video content → Watch at least 75% of the video | Progress bar advances. 'Mark as Completed' button becomes available after 75%. | Critical
41 | TC-041 | 5 – Learner (Self-Enroll) | Learner | Mark Content as Completed | Learner → Course → After watching/reading content → Click 'Mark as Completed' | Content item shows green checkmark. Progress counter updates. | Critical
42 | TC-042 | 5 – Learner (Self-Enroll) | Learner | Take and Pass Test | Learner completes all content → Test section appears → Start Test → Answer all questions correctly → Submit | Score shown. Status: Passed. Course marked as complete. Points awarded. | Critical
43 | TC-043 | 5 – Learner (Self-Enroll) | Learner | Take and Fail Test, Then Retake | Learner → Start Test → Answer incorrectly below threshold → Submit → Retake test → Pass | First attempt shows Failed. Retake is available. Second attempt shows Passed. | High
44 | TC-044 | 5 – Learner (Self-Enroll) | Learner | Submit Assignment | Learner → Course → Assignment section → Upload file to SharePoint link → Paste submission URL → Submit | Submission is recorded with status 'Submitted'. Trainer receives notification. | Critical
45 | TC-045 | 5 – Learner (Self-Enroll) | Learner | Leave Course Feedback | Learner → [Completed Course with feedback enabled] → Feedback section → Select star rating → Add comment → Submit | Feedback is saved and shown in the Trainer's Feedback tab. | Medium
46 | TC-046 | 5 – Learner (Self-Enroll) | Learner | Comment on Content | Learner → Course content → Discussion section → Type comment → Post | Comment appears in the discussion thread. | Medium
47 | TC-047 | 5 – Learner (Self-Enroll) | Learner | Reply to Comment | Learner → Discussion → Click Reply on an existing comment → Type reply → Post | Reply appears nested under the parent comment. Author is notified. | Medium
48 | TC-048 | 5 – Learner (Self-Enroll) | Learner | View Learning History | Learner → sidebar → Learning History | Completed courses grouped by pathway are shown, with completion date and test score. | High
49 | TC-049 | 5 – Learner (Self-Enroll) | Learner | Download Certificate | Learner completes ALL courses in a pathway → Open pathway → Click 'Get Certificate' → Certificate page → Click 'Download Certificate' | Certificate page shows learner name, pathway name, and completion date. Browser print dialog opens for PDF download. | Critical
▸ 6 – Manager Approval
50 | TC-050 | 6 – Manager Approval | Manager | View Team Members | Sign in as Manager → Manager → Professionals | All users assigned to this manager are listed with name, division, pathways count, and points. | Critical
51 | TC-051 | 6 – Manager Approval | Manager | Approve Pathway Request | Manager → Pathway Requests → Find pending request → Click Approve | Request status changes to Approved. Learner receives approval notification and is enrolled. | Critical
52 | TC-052 | 6 – Manager Approval | Manager | Reject Pathway Request | Manager → Pathway Requests → Find pending request → Click Reject → Enter rejection reason → Confirm | Request status changes to Rejected. Learner receives rejection notification with reason. | High
53 | TC-053 | 6 – Manager Approval | Manager | Assign Pathway to Team Member | Manager → Professionals → [Team Member] → Learning tab → Assign Pathway → Select pathway → Set deadline → Confirm | Team member is enrolled. Pathway appears in their Home dashboard. Deadline is visible. | High
54 | TC-054 | 6 – Manager Approval | Manager | Update Enrollment Deadline | Manager → Professionals → [Team Member] → Learning tab → Click edit icon next to enrollment → Update deadline → Save | Deadline is updated for that enrollment. | Medium
55 | TC-055 | 6 – Manager Approval | Manager | View Team Member Progress | Manager → Professionals → [Team Member] → View Progress | Detailed view shows enrolled pathways, course completion per pathway, and overall progress. | High
56 | TC-056 | 6 – Manager Approval | Manager | Confirm Growth Plan Goal | Manager receives notification of completed goal → Go to team member's Growth Plan tab → Click Confirm on a completed goal | Goal is marked as Confirmed. Team member receives notification. | High
57 | TC-057 | 6 – Manager Approval | Manager | View Team Analytics | Manager → Analytics → Review metrics and use filters | Shows team size, enrolments, completion rate, average points, and per-division breakdown. | Medium
▸ 7 – Growth Plan
58 | TC-058 | 7 – Growth Plan | Learner | Create Growth Plan Goal | Learner → My Growth Plan → Add Item → Enter goal title → Optionally link a pathway → Save | Goal appears in the growth plan list with status In Progress. | High
59 | TC-059 | 7 – Growth Plan | Learner | Mark Goal as Completed | Learner → My Growth Plan → Click checkmark on an in-progress goal | Goal status changes to Completed. Manager receives notification. | High
60 | TC-060 | 7 – Growth Plan | Learner | View Confirmed Goals | Learner → My Growth Plan → Check confirmed items | Confirmed goals show green 'Confirmed' badge with confirmation date. | Medium
▸ 8 – Notifications
61 | TC-061 | 8 – Notifications | Learner | Receive Enrollment Approval Notification | After manager approves enrollment → Learner checks notifications (bell icon) | Unread count badge appears. Notification reads: pathway approved. Clicking navigates to the pathway. | High
62 | TC-062 | 8 – Notifications | Learner | Receive Assignment Graded Notification | After trainer grades assignment → Learner checks notifications | Notification shows grade result (Passed/Failed). Clicking navigates to the course. | High
63 | TC-063 | 8 – Notifications | Manager | Receive Pathway Request Notification | After learner requests enrollment → Manager checks notifications | Notification shows learner name and pathway. Clicking navigates to Pathway Requests page. | High
64 | TC-064 | 8 – Notifications | Learner | Mark Notifications as Read | Learner → Notifications page → View all notifications | Unread notifications are highlighted. After visiting the page, unread count resets. | Medium
▸ 9 – Analytics
65 | TC-065 | 9 – Analytics | Admin | View Admin Analytics | Admin → Analytics → Review default view | Shows total users, enrolments, completion rate, avg points, top pathways, and global leaderboard. | High
66 | TC-066 | 9 – Analytics | Admin | Filter Analytics by Division | Admin → Analytics → Select a division from the filter | All metrics update to reflect only users in that division. | Medium
67 | TC-067 | 9 – Analytics | Admin | View Leaderboard | Learner → Home dashboard → Leaderboard widget | Top users ranked by total points are displayed. Current user's rank is highlighted. | Medium
▸ 10 – Settings
68 | TC-068 | 10 – Settings | Any | Change Password | Sidebar → Settings gear → Change Password → Enter current password → Enter new password → Confirm → Save | Password is updated. Next sign-in requires the new password. | High
69 | TC-069 | 10 – Settings | Any | View User Guide | Sidebar → Help → Select a role tab → Expand an accordion section | Step-by-step instructions are shown for the selected role and section. | Low
70 | TC-070 | 10 – Settings | Admin | Edit User Details | Admin → Users → Actions → Edit → Update name or division → Save | User details are updated in the list. | Medium
71 | TC-071 | 10 – Settings | Admin | Delete User | Admin → Users → Actions → Delete → Confirm | User is removed from the list. | Medium

## Summary
UAT Summary
Phase | Total TCs | Priority Breakdown
1 – Setup | 3 | Critical:3
2 – Admin Setup | 21 | High:9 ¦ Critical:8 ¦ Medium:4
3 – SME | 4 | High:3 ¦ Medium:1
4 – Trainer | 6 | High:4 ¦ Critical:1 ¦ Medium:1
5 – Learner (Self-Enroll) | 15 | Critical:10 ¦ High:2 ¦ Medium:3
6 – Manager Approval | 8 | Critical:2 ¦ High:4 ¦ Medium:2
7 – Growth Plan | 3 | High:2 ¦ Medium:1
8 – Notifications | 4 | High:3 ¦ Medium:1
9 – Analytics | 3 | High:1 ¦ Medium:2
10 – Settings | 4 | High:1 ¦ Low:1 ¦ Medium:2
TOTAL | 71
Priority Summary
Critical | 24
High | 29
Medium | 17
Low | 1
Sign-Off
Role | Name | Signature / Date
UAT Coordinator
HR Admin
IT / Developer
Approver